## Asbestos Register - B St C
Loocation of Asbestos Containing Material (ACM) | Type of ACM | Approx. Area of ACM | Date of Original Inspection | Date of Last Inspection | Material Assessment | Risk of Disturbance | Condition | Action
Twin leaf doors from Entrance Hall to Large Hall | Brown Asbestos | Approx. 6 m2 | 2017-05-01 | 2024-01-01 | Fair | Minimal | Already covered with hardboard, taped at open edges and painted. | Consider removal.
Minor damage to paint at open edges.
Single leaf timber door from side of Stage to adjacent Stair | White Asbestos | Approx. 3 m2 | 2017-05-01 | 2024-01-01 | Fair | Minimal | Already covered with hardboard, part painted and taped at open edge. | Requires replacement to
[7 empty] | Minor damage to paint at open edge. | replace defective self-closer.
Single leaf Fire Escape door form Inner Hall to Front Elevation | White Asbestos | Approx. 3 m2 | 2017-05-01 | 2024-01-01 | Fair | Minimal | Already covered with hardboard and painted. | Consider removal.
Minor damage to paint at edges.
Bitumen adhesive present under two layers of floor lino in | White Asbestos | Approx. 30 m2 | 2017-05-01 | 2024-01-01 | Unknown | Minimal | Satisfactory | None required at present.
Large Hall Vestibule
External soffits above the entrance to the halls and over | White Asbestos | Approx. 4 m2 | 2017-05-01 | 2024-01-01 | Fair | Minimal | Satisfactory | None required at present.
the fire escape door next to the boiler house